## Sheet1
Task ID | Tasks | Status | Comments
1 | Installation - provide & install IoT sensors, IoT gateways, & cellular/WiFi hotspots (see Deployment Plan slide for installation details and Appendix for IoT Endpoint & Gateway details) | Done
2 | Configuration - provision & configure IoT sensors, IoT gateways, and cellular/WiFi hotspots | Done
3 | Enable Cloud Service - setup all aspects of the cloud-based Preventative Maintenance Service for use at CEMEX | In Work | Sensor data is successfully being transported into the Bluzone Cloud. NEORIS has setup and verified a beta enviroment to test that this data can be successfully exported fromBluzone into Siemens Xtools, that vibration algorithms can be applied within Xtools, and that this data can be exported into Siemens MindSphere via Siemens MindConnect. We just received the MindSphere tenant from Siemens on May 10th, but were busy preparing for Sapphire and not able to continue with CEMEX setup until now. Outstanding work left to do is setup the MindSphere tenant specifically, connect up the CEMEX MindConnect Nano, then flow the CEMEX pilot data into MindSphere. ACTION: Julian is working up the estimate to complete this effort.
4 | Testing - conduct System Integration Testing to verify sensor data is properly collected in plant environment, secure transport into the cloud, and that data analysis, alerts & dashboards perform as expected. | In Work | Basic testing has been done within the Bluvision Cloud, and on the beta enviroment of MindSphere. Additional testing will need to be done once the MindSphere tenant for CEMEX is setup. Additional testing is also required once Bluvision completes their deployment of the new Machine Learning-enabled Condition Monitoring solution, and helped to configure alerts and dashboards based on the automated data analysis functionality included in the BV machine learning feature. ACTION: Craig to schedule meeting with Bluvision to identify testing timeline
5 | Perform machine learning - establish baseline machine performance, and identify & configure candidate thresholds to indicate machine failure |  | Bluvision is working on a new beta release of their Machine Learning-enabled condition monitoring solution which was recently announced. We have run some preliminary tests of this feature, and been coordinating directly with Bluvision on subsequent corrections, beta releases and testing. ACTION: Craig to schedule meeting with Bluvision to identify timeframe for when Bluvision will have this functionality in place and ready to test at CEMEX.
6 | Alerts – configure alerts for all assets which have IoT sensors installed |  | Dependency on Task IDs 3 & 5
7 | Dashboards - provide CEMEX with online access to dashboards reflecting status of all assets which have IoT sensors installed |  | Dependency on Task IDs 3 & 5
8 | Train/Support - Provide training to designated CEMEX staff on system usage, and provide technical and - customer support the duration of the pilot |  | Dependency on Task IDs 3 & 5
9 | Review - Hold meeting to present Phase 1 accomplishments and findings, and kickoff phase 2 |  | Dependency on Task IDs 3-8
10 | Duration - approximately 2 months |  | 2 months will be up on this Thursday. Note we had 2 issues causing delays: 1) Power outage at CEMEX that lasted over 1 week (2) We did not get access to the MindSphere tenant for CEMEX until May 10 (and we were fully booked since then supporting Sapphire)